## S-Goods
Procurement Plan - Goods
Procurement Entity: Mampong Technical College of Education
Budget Period:Jan-Dec 2026
Source of Funding: IGF, and GOG.
BASIC DATA | [6 empty] | TENDERING PERIOD |  |  | TENDER EVALUATION & CONTRACT AWARD
| PLAN | [6 empty] | TENDER | TEN. | [5 empty] | INSPEC.
CONTRACT PACKAGE | VS | PACKAGE NUMBER | ESTIMATED | BUDGETED AMT GHC | PR0C. | APPR./ | PREP.TEN | INVITATION | CLOSING/ | SUB. TEN | APPROVAL | CONTRACT | CONTRACT SIG. | DELIVERY | FINAL
| ACTUAL |  | AMT GH¢ |  | METH. | AUTH. | DOC. | DATE | OPEN | EVA. REPORT | DATE | DATE | SIG. | DATE | ACCEPT
Cleaning & Sanitation | Plan | AR/MTCE/GD/001/26 | 40000 | 80000 | PQ | HE | 27/03/2026 | 2026-09-04 | 23/04/26 | 30/04/26 | 2026-07-05 | 20/05/26 | 28/05/26 | 10/06/26 | 11/06/26
Materials | Actual
Stationery | Plan | AR/MTCE/GD/002/26 | 200000 | 200000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 30/04/26 | 2026-06-05 | 21/05/26 | 22/05/26 | 10/05/26 | 11/06/26
Actual
Building Materials | Plan | AR/MTCE/GD/003/26 | 70000 | 120000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 30/4/2026 | 13/05/26 | 20/05/26 | 28/05/26 | 10/06/26 | 11/06/26
Actual
Actual
Furniture & Fittings | Plan | AR/MTCE/GD/004/26 | 50000 | 50000 | PQ | HE | 2026-05-05 | 2026-07-05 | 21/05/26 | 2026-01-06 | 2026-12-06 | 22/06/26 | 24/06/26 | 09/07/26 | 10/07/26
Actual
Computer & Accessories | Plan | AR/MTCE/GD/005/26 | 100000 | 100000 | PQ | HE | 2026-05-05 | 2026-07-05 | 21/05/26 | 2026-01-06 | 2026-12-06 | 22/06/26 | 24/06/26 | 09/07/26 | 10/07/26
Actual
Office Equipment & | Plan | AR/MTCE/GD/006/26 | 50000 | 50000 | PQ | HE | 2026-05-05 | 2026-09-05 | 23/05/26 | 2026-05-06 | 2026-11-06 | 19/06/26 | 29/06/26 | 09/07/26 | 10/07/26
Accessories | Actual
Purchase of Air Condition | Plan | AR/MTCE/GD/007/26 | 50000 | 50000 | PQ | HE | 2026-01-06 | 2026-09-06 | 23/06/26 | 2026-06-07 | 13/07/26 | 20/07/26 | 29/07/26 | 10/08/26 | 11/08/26
Actual
Mercantile Food | Plan | AR/MTCE/GD/008/26 | 770000 | 780000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 2026-06-05 | 13/05/26 | 20/05/26 | 28/05/26 | 11/06/26 | 12/06/26
Actual
Domestic Food Items | Plan | AR/MTCE/GD/009/26 | 580000 | 610000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 2026-06-05 | 13/05/26 | 20/05/26 | 28/05/26 | 10/06/26 | 11/06/26
Actual
Fish and Egg Product | Plan | AR/MTCE/GD/010/26 | 180000 | 200000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 2026-06-04 | 13/04/26 | 20/04/26 | 28/04/26 | 11/05/26 | 10/06/26
Actual
Electrical Materials & Accessories | Plan | AR/MTCE/GD/011/26 | 75000 | 80000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 2026-06-05 | 13/05/26 | 20/05/26 | 28/05/26 | 09/06/26 | 10/06/26
Actual
Lubricants and Fuel | Plan | AR/MTCE/GD/012/26 | 250000 | 250000 | PQ | HE | 2026-01-04 | 2026-09-04 | 23/04/26 | 2026-06-05 | 13/05/26 | 20/05/26 | 28/05/26 | 10/06/26 | 10/06/26
Actual
Security Uniform | Plan | AR/MTCE/GD/013/26 | 30000 | 30000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Refreshment Items | Plan | AR/MTCE/GD/014/26 | 100000 | 100000 | PQ | HE | 2026-02-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Drugs | Plan | AR/MTCE/GD/015/26 | 14000 | 14000 | PQ | HE | 2026-02-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Chemicals and Consumables | Plan | AR/MTCE/GD/016/26 | 10000 | 10000 | PQ | HE | 2026-02-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Teaching Materials | Plan | AR/MTCE/GD/017/26 | 430000 | 430000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Sport, Recreational and Cultural Mat | Plan | AR/MTCE/GD/018/26 | 60000 | 60000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Office Consumable | Plan | AR/MTCE/GD/019/26 | 50000 | 50000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Clothing and Uniform for Students | Plan | AR/MTCE/GD/020/26 | 250000 | 250000 | PQ | HE | 2026-01-04 | 2026-08-04 | 20/04/26 | 24/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 27/05/26 | 29/05/26
Actual
Value Books | Plan | AR/MTCE/GD/021/26 | 2000 | 2000 | PQ | HE | 2026-01-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Household Equipments | Plan | AR/MTCE/GD/022/26 | 150000 | 150000 | PQ | HE | 2026-08-04 | 2026-09-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 17/05/26 | 28/05/26 | 29/05/26
Actual
Fire Fighting Accessories | Plan | AR/MTCE/GD/023/26 | 13000 | 13000 | PQ | HE | 2026-07-04 | 2026-10-04 | 20/04/26 | 28/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 28/05/26 | 29/05/26
Actual
Materials and Consumables for Official Celebrations | Plan | AR/MTCE/GD/024/26 | 150000 | 150000 | PQ | HE | 2026-08-04 | 2026-10-04 | 20/04/26 | 29/04/26 | 2026-08-05 | 15/05/26 | 20/05/26 | 29/05/26 | 2026-01-06
Actual
TOTAL |  |  | 3674000 | 3829000
SUMMARY
TOTAL ESTIMATE AMT |  | 3674000
TOTAL BUDGETED AMT |  | 3829000
EXPECTED VARIANCE |  | 155000

## S-Works
Procurement Entity: Mampong Technical College of Education.
Budget Period:Jan-Dec 2026
Source of Funding: IGF AND GOG
TENDER
Construction of 18 Unit Lecture Hall (Phase Four) | Plan | AR/MTCE/WK/001/26 | 1000062 | PQ | POST | HE | 2026-02-06 | 27/12/23 | 22/06/26 | 2026-03-07 | 15/7/2026
Actual
TOTAL |  |  | 1000062

## T-Services
Procurement Plan - Technical Service
Procurement Entity: | Mampong Technical College of Education.
Budget Period :January-December 2026
Source of Funding: IGF | [7 empty] | Preparation of Request for Proposals | Consultant Proposals |  | Proposal Evaluation Technical (T) & Financial (F) |  |  |  |  | Negotiations |  |  | Contract Finalization |  |  |  | Contract Implementation
Contract Packages* | Plan vs. Actual | Package Number | Estimated Amount (Cedis) | BUDJETED CEDIS | Selection Method | Final Authority for Contract Award | Plan vs. Actual | Prep & Submission by Executing Agency | Invitation Date | Submission/ Opening Date | Complete Evaluation Report (T) | Opening Financial Proposals | Complete Eval Report (T) (F) | Approval of Eval Report (T) (F) | Plan vs. Actual | Negotiations | Submission Draft Contract | Approval of Negotiation report | Contract Amount (Cedis) | Contract ward | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost
1 .Repairs of Computers, Printers & Photocopiers | Plan | AR/MTCE/TS/001/26 | 45000 | 45000 | PQ | HOE | Plan | 25/3/2026 | 2026-02-04 | 17/4/2026 | 22/4/2026 | 28/4/2026 | 2026-04-05 | 6/05/26 | Plan | 08/05/2026 | 12/05/2026 | 14/05/2026 | 45000 | 19/05/2026 | 19/05/2026 | Plan | NA | 28/05/26 | 04/06/26 | 45000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
2. Maintenance of Official Vehicles | Plan | AR/MTCE/TS/002/26 | 100000 | 158000 | NCT | HOE | Plan | 2026-05-01 | 2026-10-01 | 23/01/26 | 2026-07-02 | 17/2/2026 | 20/02/26 | 2/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 100000 | 31/03/2026 | 07/04/2026 | Plan | NA | 28/04/26 | 4/05/26 | 90000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
3 Installation of Smoke Detectors | Plan | AR/MTCE/TS/003/26 | 5000 | 5000 | PQ | HOF=E | Plan | 2026-05-01 | 2026-12-01 | 26/01/26 | 2026-05-02 | 19/2/2026 | 23/02/26 | 26/02/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 5000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 4/05/26 | 5000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
4. Installation of Speakers & Projectors in Classrooms | Plan | AR/MTCE/TS/004/26 | 17000 | 17500 | PQ | HOE | Plan | 2026-05-01 | 2026-08-01 | 23/01/26 | 2026-05-02 | 13/2/2026 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 13/03/2026 | 24/03/2026 | 15000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 4/05/26 | 15000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
5 . Servicing/ Repairs of Aircondition | Plan | AR/MTCE/TS/005/26 | 30000 | 35000 | PQ | HOE | Plan | 2026-05-01 | 2026-08-01 | 23/01/26 | 2026-05-02 | 13/2/2026 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 30000 | 31/03/2026 | 7/04/2026 | 30000 | NA | 28/04/26 | 5/05/26 | 27000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
6. Collection of Solid Waste* part of sanitation | Plan | AR/MTCE/TS/006/26 | 12000 | 12000 | PQ | HOE | Plan | 2026-05-01 | 2026-08-01 | 20/01/26 | 2026-05-02 | 14/2/2026 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 12000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 5/05/26 | 12000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
7. Dislodging of Liquid Waste* part of sanitation | Plan | AR/MTCE/TS/007/26 | 10000 | 10000 | PQ | HOE | Plan | 2026-06-01 | 2026-09-01 | 21/01/26 | 2026-07-02 | 2026-12-02 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 10000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 5/05/26 | 10000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
9.Refill and Servicing of Fire Extinguishers | Plan | AR/MTCE/TS/008/26 | 13000 | 13000 | PQ | HOE | Plan | 2026-06-01 | 2026-09-01 | 22/01/26 | 2026-05-02 | 2026-11-02 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 13000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 8/05/26 | 15000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
10.Purchase of Palm Kennel & Servicing of Stove | Plan | AR/MTCE/TS/009/26 | 60,000.. | 65000 | PQ | HOE | Plan | 2026-01-04 | 2026-08-04 | 27/04/26 | 2026-11-05 | 16/2/2026 | 20/05/26 | 3/06/26 | Plan | 10/06/2026 | 17/06/2026 | 24/6/2026 | 50000 | 30/06/2026 | 3/07/2026 | Plan | NA | 28/07/26 | 8/08/26 | 45000
| Actual |  |  |  | . |  | Actual | [7 empty] | Actual | [6 empty] | Actual
11. Water Quality Test | Plan | AR/MTCE/TS/0010/26 | 3000 | 3000 | PQ | HOE | Plan | 2026-06-01 | 2026-08-01 | 22/01/26 | 2026-07-02 | 16/2/2026 | 19/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 3000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 8/05/26 | 3000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Library Automation | Plan | AR/MTCE/TS/011/26 | 50000 | 50000 | PQ | HOE | Plan | 2026-01-04 | 2026-08-04 | 27/04/26 | 2026-11-05 | 16/2/2026 | 20/05/26 | 3/06/26 | Plan | 10/06/2026 | 17/06/2026 | 24/6/2026 | 50000 | 30/06/2026 | 07/07/2026 | Plan | NA | 28/07/26 | 07/08/26 | 45000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Fumigation of Halls of Residence | Plan | AR/MTCE/TS/012/26 | 15000 | 15000 | PQ | HOE | Plan | 2026-01-04 | 2026-08-04 | 27/04/26 | 2026-11-05 | 16/2/2026 | 20/05/26 | 3/06/26 | Plan | 10/06/2026 | 17/06/2026 | 24/6/2026 | 15000 | =U36 | 07/07/2026 | Plan | NA | 28/07/26 | 6/08/26 | 15000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Maintenance of Funiture &Fittings | Plan | AR/MTCE/TS/013/26 | 40000 | 50000 | PQ | HOE | Plan | 2026-05-01 | 2026-08-01 | 22/01/26 | 2026-07-02 | 14/2/2026 | 19/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 40000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 7/05/26 | 40000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Website Hosting | Plan | AR/MTCE/TS/014/26 | 5000 | 5000 | PQ | HOE | Plan | 2026-02-01 | 2024-09-01 | 23/01/24 | 2024-08-02 | 16/2/2024 | 23/02/24 | 3/03/24 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 5000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 7/05/26 | 5000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
ECG (Prepaid & Postpaid Credit) | Plan | AR/MTCE/TS/015/26 | 280000 | 300000 | PQ | HOE | Plan | 2026-02-01 | 2026-09-01 | 23/01/26 | 2026-07-02 | 13/2/2026 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 280000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 11/05/26 | 100000
| Actual | [5 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Repairs of Mowers & Slashers | Plan | AR/MTCE/TS/016/26 | 20000 | 20000 | PQ | HOE | Plan | 2026-02-01 | 2026-09-01 | 23/01/26 | 2026-07-02 | 13/2/2026 | 20/02/26 | 3/03/26 | Plan | 10/03/2026 | 17/03/2026 | 24/03/2026 | 20000 | 31/03/2026 | 7/04/2026 | Plan | NA | 28/04/26 | 11/05/26 | 20000
| Actual | [5 empty] | Actual
Medicals | Plan | AR/MTCE/TS/016/26 | 80000 | 80000 | PQ | HOE | Plan | 2026-02-01 | 2026-07-02 | 13/2/2026 | 16/2/2026 | 13/02/26 | 23/02/26 | 02/03/2026 | Plan | 4/03/2026 | 80000 | 10/03/2026 | 17/03/2026 | 20/03/2026 | NA | Plan | 26/03/26 | 80000 | 30/03/26 | 80000
Actual
Consultancy Services | Plan | AR/MTCE/TS/016/26 | 20000 | 20000 | PQ | HOE | Plan | 2026-02-04 | 2026-07-04 | 13/4/2026 | 20/04/26 | 30/04/26 | 14/05/26 | 21/05/2026 | Plan | 27/05/2026 | 20000 | 30/05/2026 | 02/06/2026 | 3/06/2026 | NA | Plan | 09/06/26 | 20000 | 15/06/26 | 20000
Creation of Electronic Support unit for the Library | Plan | AR/MTCE/TS/016/26 | 100000 | 100000 | PQ | HOE | Plan | 2026-02-04 | 2026-07-04 | 13/4/2026 | 20/04/26 | 30/04/26 | 14/05/26 | 21/05/2026 | Plan | 27/05/2026 | 100000 | 30/05/2026 | 02/06/2026 | 3/06/2026 | NA | Plan | 09/06/26 | 100000 | 15/06/26 | 100000
Actual
Repair of Residential Building | Plan | AR/MTCE/TS/016/26 | 100000 | 100.000.00 | PQ | HOE | Plan | 2026-02-04 | 2026-07-04 | 13/4/2026 | 20/04/26 | 30/04/26 | 14/05/26 | 21/05/2026 | Plan | 27/05/2026 | 100000 | 30/05/2026 | 02/06/2026 | 3/06/2026 | NA | Plan | 09/06/26 | 100000 | 15/06/26 | 100000
TOTAL |  |  |  | 1081500 | [15 empty] | Ms. Gifty Dwomoh
SUMMARY
ESTIMATED AMT |  | 0
BUDGETED AMT |  | 1081500
VARIANCE |  | 1081500
5 . Servicing/ A1:AA68+A57:T68Repairs of Aircondition